## Sheet1
As a Graduate |  | Complete | Outstanding |  | As a Manager |  | Complete | Outstanding
1 | I want to login to the system and view my dashboard | Almost | Styling | Styling | 1 | I want to login to the system and view my dashboard | No
2 | I want to be able to view my current and past rotations | Almost | Styling | Styling | 2 | I want to be able to view which graduates are currently in my area | No
3 | I want to be able to view my goals set for current and past rotations | Almost | Styling | Styling | 3 | I want to be able to view details about a graduate | No
4 | I want to be able to view Areas that I could rotate into | Almost | Styling | Styling | 4 | I want to be able to view details about projects | No
5 | I want to view projects I could request to work on | Almost | Styling | Styling | 5 | I want to be able to modify details about projects I own | No
6 | I want to view managers that whose areas I could potentially work in | Almost | Styling | Styling | 6 | I want to be able to create new projects in my area | No
7 | I want to create new goals for my current rotation | Almost | Styling |  | 7 | I want to be able to view applications to join a project | No
8 | I want to edit goals for my current rotation | Almost | Styling |  | 8 | I want to be able to remove projects that are no longer active | No
9 | I want to be able to apply to join a project | Almost | Redirect to GraduatProjectWishLists page for graduate wishlist view Indicate if request on project has previously been sent Styling |  | 9 | I want to be able to make comments on the goals of a graduates rotation | No
10 | I want to be able to update my information | No |  |  | 10 | I want to be able to set goals for a rotation | No
Extras
Add direct managers to the system to comment on goals and progress (E.G. Justin Pike)
DB change | Add office type to areas
DB change | Add extra feedback to goals to cater for manager and graduate feedback
DB change | Add start and end date to rotations table for rotation period